## Time_table
Working Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Start of the week | 2025-11-25 | 2025-12-02 | 2025-12-09 | 2025-12-16 | 2025-12-23 | 2025-12-30 | 2026-01-06 | 2026-01-13 | 2026-01-20 | 2026-01-27 | 2026-02-03 | 2026-02-10 | 2026-02-17 | 2026-02-24 | 2026-03-03 | 2026-03-10 | 2026-03-17 | 2026-03-24 | 2026-03-31 | 2026-04-07 | 2026-04-14 | 2026-04-21 | 2026-04-28 | 2026-05-05 | 2026-05-12 | 2026-05-19
Sensing and input working package | 2025-11-25: Documentation on the given guides and projects. Chose main languages and technologies Create/adapt project plan Members tasks asignation; 2025-12-02: Camera handling, preprocessing, noise cancelling, ROIs definition; 2026-01-27: Define other necessary sensors, define use-case, integration (IMU, distance), preprocessing, noise cancelling.; 2026-05-19: BFMC
Define use-case and test given servers information (localisation on map, cars interaction, gps interaction)
[19 empty] | Induce noise on all sensors and systems |  |  |  | Other functionalities and optimizations
Perception and scene understanding working package | 2025-12-02: Lane detection; 2026-02-03: Traffic sign detection; 2026-03-03: Traffic light detection
[13 empty] | Position fusion | [5 empty] | Traffic lights detection & classification
[15 empty] | Define objects properties file |  |  |  | Object detection & classification
Environmental server interaction
Other functionalities and optimizations
Behaviour and motion plan working package | 2025-12-02: Define project architecture and communication between packages; 2026-02-03: Define path planning and validation; 2026-03-03: Define robustness and safety measures
Define decision making --> priorities of actions and state flow
[19 empty] | Induce noise on systems to valdiate robustness (loss of image, burned image, road search, undefined objects and states) |  |  |  | Other functionalities and optimizations
Vehicle control working packages | 2025-12-02: Lane following and speed control; 2026-02-03: Intersection navigation; 2026-03-03: Simpla action taking maneuvers (parking, stop for traffic sign, stop for traffic light, stop for pedestrian); 2026-03-31: Complex action taking maneuvers (swith lane for static and mobile car, road search)
Other functionalities and optimizations
Final result & Demo | 2025-11-25: Team can control the phisical car remotely and the virtual car on the simulator.; 2025-12-02: Robot can keep a lane, can make a curve; 2026-02-03: Robot can navigate in intersection; 2026-03-03: Robot can go on a pre-determined path, stop at stop sign, park at parking sign, slow at crosswalk; 2026-03-31: While detecting and calculating it's position, the robot can dynamicaly go to specified checkpoint, react to traffic lights, interact with other cars and send environemt data)
|  | Team defines and creates its own physical testing environment |  |  |  | Team defines a way of parallel developing and testing
Team installs the virtual testing environment
Other functionalities and optimizations
Deadlines | 2025-12-16: 2025-12-22; 2026-02-03: 2026-02-06; 2026-03-10: 2026-03-09; 2026-04-07: 2026-04-13; 2026-05-19: 2026-05-21
Checkpoint | 2025-12-16: 1st report; 2026-02-03: 2nd report; 2026-03-10: Mid-term quality gate; 2026-04-07: 3rd report; 2026-05-19: Finals